## Hisstorias de Usuario
ITEM | Requirement | FOR WHO (USER) | What (NEED) | PARA QUE (SOLUCIÓN) | COMO (DESCRIPCIÓN DE TAREAS) | DONE BY WHO(RESPONSIBLE PROGRAMMER) | HOW LONG (ESTIMATED IN HRS) | Priority | STATUS | Test (AS IT TURNS OUT) | Guest reviews
C-101 | creation menu Admin | customer | Enter the program with a username and password | to prevent external agents from entering the registry and manipulating data | Implementing a function that does not allow entry until the correct user and password is placed | Gabriel | 2 | alta | Terminado | Validating password entry, if all 3 attempts are finished, the program closes, if the login is successful, it moves to the program's use
C-102 | creation of function to create text file | customer | So that the information is saved in a text file and is easy to view | In this way the user will be able to access a folder where all the logs are saved and observe the information | Encoding the function that allows us to open the file | Josue | 2 | Alta | Terminado | If at the time of running the program and select option 1 from the menu, we save that record, a text file containing that record must be created
C-103 | creation of the function to delete record | customer | In case there is a need to delete a record | If a record is with information that is incorrect or expires, it will allow that record to be deleted | Using the functions structure and the steps to follow to encode the function of deleting record | Kevin | 3 | Alta | Terminado | In the text file that is created we should observe if that record is no longer this, if so, then the function is correctly implemented
C-104 | creation of the function to add record | customer | With this option it will be easier to add the desired information | In case the Administrator wants to know how to add information | With the functions of adding | Jhoel | 2 | Alta | Terminado | When you press the query option of the menu, a message should appear to us of the number of the house that we want to search, when entering it we must appear all your information
C-105 | create the function to modify the record | customer | With this function you can modify certain data | In case there's been any error in data entry | With the functions of modifying | Alisson | 3 | alta | Terminado | By selecting the option to modify, it will allow us to modify the data of the record that we want, if the information is saved then it is valid
C-106 | save to the data in a text file | customer | so dynamically you can use the data | For better data management and to be able to use it at will | implementing text files | Gabriell | 3 | alta | Terminado | When you ask for the matrix to be printed, the records that we have previously saved should appear
C-107 | show the movies | customer | show the list of available movies | The purpose of the project is this, so you can observe the available films | Adding the elements | Josue | 2 | alta | Terminado | If the integer records that are in a row are sued and their result gives as it is, then that function is well implemented
C-108 | show promotions | customer | show the list of promotions | To show homeowners what value they must pay for graduates | adding the row where the promotion is | Kevin | 2 | alta | Terminado | If the records in which the egress are located are in a row of the matrix, the total value to be paid for each dwelling must be added up and taken out
C-109 | show the price of the seat and the room | customer | show the dollar value of the seat and the room | To be able to observe the values so that we can take a budget | adding the row where the seat and the room are located | Jhoel | 3 | alta | Terminado | If selecting the report option should display all previously stored information, the function is well implemented
C-110 | show the ticket | customer | show the name of the movie, the number and value in dollars of the seat and the room, the key of the ticket | The purpose of the project is this, so you can know the information of the ticket | adding the row where the ticket is located | Alisson | 2 | alta | Terminado

## Historia de Usuario
ITEM | C-102 |  | USUARIO | customer | STATUS | Terminado |  | PRIORIDAD | Alta
NOMBRE HISTORIA |  | creation of function to create text file |  |  |  | PROG. RESP | Josue
QUE | So that the information is saved in a text file and is easy to view |  |  |  |  | PARA QUE |  | In this way the user will be able to access a folder where all the logs are saved and observe the information
COMO | Encoding the function that allows us to open the file
PRUEBA |  | If at the time of running the program and select option 1 from the menu, we save that record, a text file containing that record must be created
ITEM | C-103 |  | USUARIO | customer | STATUS | Terminado |  | PRIORIDAD | Alta
NOMBRE HISTORIA |  | creation of the function to delete record |  |  |  | PROG. RESP | Kevin
QUE | In case there is a need to delete a record |  |  |  |  | PARA QUE |  | If a record is with information that is incorrect or expires, it will allow that record to be deleted
COMO | Using the functions structure and the steps to follow to encode the function of deleting record
PRUEBA |  | In the text file that is created we should observe if that record is no longer this, if so, then the function is correctly implemented
ITEM | C-104 |  | USUARIO | customer | STATUS | Terminado |  | PRIORIDAD | Alta
NOMBRE HISTORIA |  | creation of the function to add record |  |  |  | PROG. RESP | With the functions of adding
QUE | With this option it will be easier to add the desired information |  |  |  |  | PARA QUE |  | In case the Administrator wants to know how to add information
COMO | With the functions of adding
PRUEBA |  | When you press the query option of the menu, a message should appear to us of the number of the house that we want to search, when entering it we must appear all your information
ITEM | C-105 |  | USUARIO | customer | STATUS | Terminado |  | PRIORIDAD | alta
NOMBRE HISTORIA |  | create the function to modify the record |  |  |  | PROG. RESP | With the functions of modifying
QUE | With this function you can modify certain data |  |  |  |  | PARA QUE |  | In case there's been any error in data entry
COMO | With the functions of modifying
PRUEBA |  | By selecting the option to modify, it will allow us to modify the data of the record that we want, if the information is saved then it is valid
ITEM | C-108 |  | USUARIO | customer | STATUS | Terminado |  | PRIORIDAD | alta
NOMBRE HISTORIA |  | show promotions |  |  |  | PROG. RESP | adding the row where the promotion is
QUE | show the list of promotions |  |  |  |  | PARA QUE |  | To show homeowners what value they must pay for graduates
COMO | adding the row where the promotion is
PRUEBA |  | If the records in which the egress are located are in a row of the matrix, the total value to be paid for each dwelling must be added up and taken out
ITEM | C-109 |  | USUARIO | customer | STATUS | Terminado |  | PRIORIDAD | alta
NOMBRE HISTORIA |  | show the price of the seat and the room |  |  |  | PROG. RESP | adding the row where the seat and the room are located
QUE | show the dollar value of the seat and the room |  |  |  |  | PARA QUE |  | To be able to observe the values so that we can take a budget
COMO | adding the row where the seat and the room are located
PRUEBA |  | If selecting the report option should display all previously stored information, the function is well implemented
HISTORIA DE USUARIO
HISTORIA DE USUARIO
HISTORIA DE USUARIO
HISTORIA DE USUARIO
HISTORIA DE USUARIO
HISTORIA DE USUARIO

## Planificacion
Plan for project implementation
¿What? | ¿Who? | ¿How? | ¿From? | Checkpoint | Date | Status
1. Project Definition ( Cinema Box Office (Online)) | Aguirre Gabriel Alemán Josué Chicaiza Jhoel Chuquimarca Kevin Clavijo Alisson | Brainstorming | 2020-06-05 | Meet | 2020-06-06 | Approved
2. Present idea to the teacher | Aguirre Gabriel Alemán Josué Chicaiza Jhoel Chuquimarca Kevin Clavijo Alisson | Explaining to the teacher | 2020-06-08 | Meet | 2020-06-10 | Approved
3. Investigation | Aguirre Gabriel Alemán Josué Chicaiza Jhoel Chuquimarca Kevin Clavijo Alisson | investigate the features and everything related to a system. | 2020-06-11 | Meet | 2020-06-13 | Approved
4. Creating Use class diagram | Aguirre Gabriel Alemán Josué Chicaiza Jhoel Chuquimarca Kevin Clavijo Alisson | Drawing up the diagram | 2020-06-14 | Meet | 2020-06-15 | Approved
5. Creating class diagram | Aguirre Gabriel Alemán Josué Chicaiza Jhoel Chuquimarca Kevin Clavijo Alisson | Developing the code and testing | 16//2020 | Meet | 2020-06-16 | Approved
6. Package Creation | Chuquimarca Kevin | Developing the code and testing | 2020-06-17 | Meet | 2020-06-17 | Approved
7. Creation Classes | Chuquimarca Kevin | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Approved
7.1Creation Class Bilboard | Alemán Josué | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Approved
7.2 Creation de menu Admin y Custumer | Alemán Josué | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Approved
7.3 Creation Class Movie | Chicaiza Jhoel | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Approved
7.4 Creation Class Room | Clavijo Alisson | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Aprobado
7.5 Creation Class Seat | Clavijo Alisson | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Aprobado
7.6 Creation Class PremierMovie | Chuquimarca Kevin | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Aprobado
7.7 Creation Class Promotion | Alemán Josué | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Aprobado
7.8 Creation Class FoodCombo | Aguirre Gabriel | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Aprobado
7.9Cration PricePurchase | Chuquimarca Kevin | Developing the code and testing | 2020-06-23 | Meet | 2020-06-23 | Aprobado
7.10 Creation Class Ticket | Aguirre Gabriel | Developing the code and testing | 2020-06-24 | Meet | 2020-06-24 | Aprobado
7.10 Creation Class Payment | Chicaiza Jhoel | Developing the code and testing | 2020-06-24 | Meet | 2020-06-24 | Aprobado
8. Creation FileManager | Chuquimarca Kevin | Developing the code and testing | 2020-06-24 | Meet | 2020-06-24 | Aprobado
9.First Cinema Prototype | Aguirre Gabriel Alemán Josué Chicaiza Jhoel Chuquimarca Kevin Clavijo Alisson | Developing the code and testing | 2020-06-24 | Meet | 2020-06-24 | Approved
10.Project presentation OBJECT-ORIENTED PROGRAMMING | Aguirre Gabriel Alemán Josué Chicaiza Jhoel Chuquimarca Kevin Clavijo Alisson | code presentation | 2020-06-25 | Meet | 2020-06-25 | Look forward

## Cronograma
Checklist de requisitos funcionales
Cronograma por realizar
1. Definición del juego a desarrollar | Actividades | Enero
2. Presentar idea al docente | Semanas | 1 | 2 | 3 | 4 | 5
3. Entrevista | 1. Definicion del proyecto ( Sistema Contable de un conjunto) | ¦
4. Creación del menú | 2. Presentar idea al docente
5. Primer prototipo de la partida del juego | 3. investigacion
6. Implementación del menú en consola gráfica | 4. Creación del menú de Registro(Usuario y contraseña)
7. Objetos de la partida en la consola gráfica | 5. Creación del menú de Datos(Ingresos, Egresos)
6. Creacion de funcion para crear archivo de texto
7. Creacion de la funcion para eliminar registro
8. Creacion de la funcion para consulta
9. Crear la funcion para modificar
10.Guardar en esos datos en una matriz
11.Mostrar la alicuota y el total de ingresos
12.Mostrar los egresos y el total de estos
13.Mostrar los ingresos y los egresos
14. Primer prototipo del Sistema Contable
15. Implementación del menú en consola gráfica
16.Presentacion de proyecto FUNDAMENTOS DE INGENIERIA DE SOFTWARE
17.Presentacion de proyecto FUNDAMENTOS DE PROGRAMACION